## Slide 1: Team 38: Virtual Try-On Clothing Bi-Weekly Update 3 Robin Martinez, Alan Vela, Jorge Olivares Sponsor: Pranav Dhulipala TA: Fardeen Mozumder
Notes: Michelle

## Slide 2: Project Summary
Waste material reduction for companies producing apparel.
Our application is going to be an accessible tool for consumers shopping online for clothing. This tool will create an avatar based on the video provided and it will be able to change between clothes.

## Slide 3: Subsystem Overview
GUI Application:
  Displays the user with the application
  Uploads and receives user information to a database
Database:
  Stores the user’s information together with their avatar
  Supply different options offered for the avatar to change clothes
Neural Network:
  Receives a .mp4 video from the database
  Returns a clothed 3D model of the user in .obj format
Shape Representation
Convolutional Architecture
Loss Function
Optimization
Clothing Database
Neural Network
GUI
App
Design
Robin | Alan | Jorge

## Slide 4: Project Timeline
08/31 | 09/14 | 09/28 | 10/12 | 10/26 | 11/16
Setting up Olympus server | ML algorithm set up and ready to work on server | ML algorithm training the model | ML algorithm training the model | Implement ML model into application | Testing application with ML model and bug fixing.
Verify GUI and database are working | GUI properly communicating with the database | GUI able to write and read database | Testing application on phone and bug fixing | Implement ML model into application | Testing application with ML model and bug fixing.
Completed | In-progress | Not Started

## Slide 5: GUI Application - Alan Vela
Accomplishments since last presentation 13 hrs | Ongoing progress/problems and plans until the next presentation
Created an avatar display page Created video display page Created clothing for the database | Write non-string data to database

## Slide 6: GUI Application - Alan Vela
Removed local storage
drive & githubs for
video/upload images
Not many changes for
GUI more integration with
database

## Slide 7: Cloud Database - Jorge Olivares
Accomplishments since last presentation 5 hrs | Ongoing progress/problems and plans until the next presentation
Created new app. New app writes users to database | GUI able to write non-string data and read data to/from database

## Slide 8: Cloud Database
Create upload class for non-string data
Work on the features of the new app.

## Slide 9: Execution Plan
 | 09/05 | 09/12 | 09/19 | 09/26 | 10/3 | 10/10 | 10/17 | 10/24 | 10/31 | 11/7
Setting access and connection to Olympus |  |  |  |  |  |  |  |  |  | 
Prepare budget and approve for parts |  |  |  |  |  |  |  |  |  | 
Get the GUI writing on database |  |  |  |  |  |  |  |  |  | 
Set up algorithm on Olympus |  |  |  |  |  |  |  |  |  | 
Create a catalog for the avatar |  |  |  |  |  |  |  |  |  | 
Write .obj and .png files into database |  |  |  |  |  |  |  |  |  | 
Train Model |  |  |  |  |  |  |  |  |  | 
GUI reading information from database |  |  |  |  |  |  |  |  |  | 
Display clothing catalog and dummy model |  |  |  |  |  |  |  |  |  | 
Test app on phone and bug fix |  |  |  |  |  |  |  |  |  | 
Create app package with ML model |  |  |  |  |  |  |  |  |  | 
Test app on phone with ML model and bug fix |  |  |  |  |  |  |  |  |  | 
Completed | In-progress | Not Started

## Slide 10: Validation Plan
Test Name | Criteria | Owner | Status
Server ready for the ML algorithm | Access granted and connection established with the server | Robin | Tested
GUI writing to the database | User information stored in the database | Jorge,Alan | Testing
ML algorithm ready for training | Test machine learning algorithm to see the proper file is delivered (.obj) | Robin | Untested
GUI reading and displaying information | Retrieval of clothing options to the GUI and displaying a catalog | Jorge,Alan | Untested
Test app without model integration | Run the application on an actual phone and test it for possible bugs. | Jorge,Alan | Untested
Train the model | Run the machine learning algorithm through Pytorch and check outputs to view progress | Robin | Untested
Deploy trained model into application | Test the model receiving input from the application and change clothes | Group | Untested
Test application with model integration on phone | Run the application on actual phone with video input and test for possible bugs | Group | Untested
Completed | In-progress | Not Started

## Slide 11
Questions?